## Sheet1
[Loftus frukt og saft] Project Schedule
Project Start date: Monday 18.11.2019
Project End date: Friday 29.11.2019
Iteration Meetings(30 minutes): Every Monday 08:00 (For Developers)
Daily Standups(10 minutes): Every day at 10:00 (For developers and stakeholders)
[5 empty] | Week 1 | [6 empty] | Week 2
TASK | LEAD | START | END | DAYS | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
[Purchase/Products] |  |  | - |  | m | t | w | t | f | s | s | m | t | w | t | f | s | s
Make a list of the products | Jonas(Front-end) | 2019-11-18 | 2019-11-20 | 3 | bar: m to w
Make a dropdown menu to order the items | Jonas(Front-end) | 2019-11-21 | 2019-11-22 | 2 | bar: t to f
Make a map addon for the procucts with google maps for costumers to see where they can buy. | Mary(Front-end) | 2019-11-18 | 2019-11-19 | 2 | bar: m to t
Make sure the map shows a nearest to me button. | Mary(Front-end) | 2019-11-20 | 2019-11-20 | 1 | bar: w
[The company] |  |  | -
Make a company information, and production page. | Mary(Front-end/copywriter) | 2019-11-21 | 2019-11-27 | 5 | bar: t to f; m to w
Make a contact form on the same page. | Mary(Front-end) | 2019-11-28 | 2019-11-29 | 2 | bar: t to f
Add links to the company facebook page. | Jonas(Front-end) | 2019-11-25 | 2019-11-25 | 1 | bar: m
[Products] |  |  | -
Add pictures and all other essential information to the list of products | Jonas(Front-end/photo) | 2019-11-26 | 2019-11-29 | 4 | bar: t to f